## backlog
| jour | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Sommaire effort restant | [5 empty] | 170 | 165 | 162 | 158 | 158 | 147 | 147 | 144 | 139 | 135 | 131 | 126 | 121 | 112 | 103 | 90 | 90 | 83 | 74 | 71 | 42 | 33
| Sommaire efforts dépensé | [5 empty] | 9 | 6 | 4 | 4 | 12 | 6 | 11 | 13 | 8 | 4 | 10 | 9 | 9 | 15 | 14 | 12 | 11 | 13 | 13 | 29 | 0 | 0 |  |  |  | 212
Sprint 1 : Mettre en place les fonctionnalités de base pour l’authentification, la gestion du profil, des cours, des échéances, du calendrier et des notifications d’un système académique et financier.
Numéro item product backlog |  | Équipe |  |  |  |  | 1: jours du sprint / (effort restant estimé en début de journée ¦ heures travaillées ce jour) | [23 empty] | Total pour tâche | Total pour tâche par membre équipe
| Cas d'utilisation ou user-story/tâche | [5 empty] | 1: 0; 2: 1; 4: 2; 6: 3; 8: 4; 10: 5; 12: 6; 14: 7; 16: 8; 18: 9; 20: 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | Oryna | Romuald | Kenny | Aziz | Joana
|  | Oryna | Aziz | Romuald | Kenny | Joana | 176 | 170 | 9 | 165 | 6 | 162 | 4 | 158 | 4 | 158 | 12 | 147 | 6 | 147 | 11 | 144 | 13 | 139 | 8 | 135 | 4 | 131 | 10 | 126 | 9 | 121 | 9 | 112 | 15 | 103 | 14 | 90 | 12 | 90 | 11 | 83 | 13 | 74 | 13 | 71 | 29 | 42 |  | 33 | 233 | 56 | 69 | 41 | 43 | 24
1 | Authentification utilisateur | 100%
| Création de la page de connexion | 100% | 0% | 0% | 0% | 0% | 8 | 8 | 2 | 6 | 1 | 5 | 0 | 5 | 0 | 5 | 1 | 4 | 0 | 4 | 0 | 4 | 1 | 3 | 0 | 3 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
| Creation de la page d'inscription | 100% | 0% | 0% | 0% | 0% | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 1 | 7 | 2 | 5 | 1 | 4 | 3 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
| Validation | 100% | 0% | 0% | 0% | 0% | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 2 | 3 | 1 | 2 | 0 | 2 | 2 | 4 | 2 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 9 | 9 | 0 | 0 | 0 | 0
| Setup de Xcode | 100% | 0% | 0% | 0% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0
2 | Création du profil d'utilisateur | 100%
| Création de la page principal pour afficher les options pour utilisateur | 100% | 0% | 0% | 0% | 0% | 6 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 0
| Ajouter la possiblité de faire les changements dans le dossier (ex:ajouter image profil, dark mode, profile details) | 100% | 0% | 0% | 0% | 0% | 6 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 4 | 4 | 0 | 0 | 0 | 0
| Visualisation du menu pour utilisauter | 100% | 0% | 0% | 0% | 0% | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 3 | 3 | 0 | 0 | 0 | 0
| Creation de la base de données pour sauvegarder les information personnels | 100% | 0% | 0% | 0% | 0% | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 4 | 4 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0
3 | Gestion du cours (ajout) |  |  |  |  | 100%
| Ajouter cours (code, nom) | 0% | 0% | 0% | 0% | 100% | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 7 | 1 | 6 | 0 | 6 | 0 | 6 | 1 | 5 | 3 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 1 | 1 | 0 |  | 0 |  | 0 | 9 | 0 | 0 | 0 | 0 | 9
| Sauvegarder le cours | 0% | 0% | 0% | 0% | 100% | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3
| Afficher la liste des cours après ajout | 0% | 0% | 0% | 0% | 100% | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
pour sprint2 | (Souhaité) Trier les cours selon le nombre d’évaluations ou l’évaluation la plus proche (sera fait quand les échéances seront prêtes) | 0% | 0% | 0% | 0% | 100% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
4 | Gestion du seuil du passage |  |  |  |  | 100%
| Attribuer un pourcentage de passage à un cours | 0% | 0% | 0% | 0% | 100% | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 |  | 0 | 4 | 0 | 0 | 0 | 0 | 4
pour sprint2 | Calculer automatiquement le minimum requis pour passer le cours selon les notes déjà obtenues. | 0% | 0% | 0% | 0% | 100% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
5 | Gestion du cours(suppression ou modification) |  |  |  |  | 100% | [46 empty] | 0 | 0
| Modifier un cours existant | 0% | 0% | 0% | 0% | 100% | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 2 | 0 |  | 0 |  | 0 |  | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Supprimer un cours (ex. abandonné) | 0% | 0% | 0% | 0% | 100% | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 2 | 0 |  | 0 |  | 0 | 2 | 0 | 0 | 0 | 0 | 2
6 | Ajout des échéances |  |  |  | 100%
| Connexion à la bd via API supabase | 0% | 0% | 0% | 100% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0
| Setup de Android studio | 0% | 0% | 0% | 100% | 0% | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 2 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
| Création de la page des échéances | 0% | 0% | 0% | 100% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 2 | 3 | 0 | 3 | 2 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7 | 0 | 0
| Création de l'ajout des échéances | 0% | 0% | 0% | 100% | 0% | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 2 | 6 | 0 | 6 | 3 | 3 | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0
7 | Modification des échéances |  |  |  | 100%
| Ajout de modification des échéances | 0% | 0% | 0% | 100% | 0% | 6 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 2 | 4 | 0 | 4 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 7 | 0 | 0
| Ajout de suppression des échéances | 0% | 0% | 0% | 100% | 0% | 6 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 1 | 5 | 0 | 5 | 1 | 4 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
8 | Vue calendrier hebdomadaire : Affichage des examens, quiz, paiement à travers une globale du calendrier | 25% | 75%
| Création du calendrier basique | 0% | 100% | 0% | 0% | 0% | 5 | 5 | 1 | 4 | 0 | 4 | 0 | 4 | 3 | 5 | 0 | 5 | 0 | 5 | 3 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 3 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0
| Ajout de la rubrique évènements à venir | 0% | 100% | 0% | 0% | 0% | 4 | 4 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0
| Création de la vue globale | 25% | 75% | 0% | 0% | 0% | 5 | 5 | 1 | 4 | 1 | 3 | 0 | 3 | 0 | 3 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 6 | 0
| Ajout de la possibilité de voir les évènements directement sur le calendrier | 0% | 100% | 0% | 0% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 1 | 4 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0
9 | Ajout de la personnalisation du calendrier avec des couleurs au choix | 25% | 75%
| Ajout du bouton de personnalisation | 25% | 75% | 0% | 0% | 0% | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 8 | 2 | 0 | 0 | 6 | 0
| Ajout des couleurs aux choix | 0% | 100% | 0% | 0% | 0% | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0
| Ajout de modifications de la police, gras, taille des lettres | 0% | 100% | 0% | 0% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 2 | 3 | 3 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0
10 | Mise en place de la notifiaction | 25% |  | 75%
| Ajouter la possbilité d'avoir les notifiacations qui sont envoyer par le systeme | 0% | 0% | 100% | 0% | 0% | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 6 | 6 | 5 | 5 | 4 | 2 | 2 | 2 | 0 | 0 | 4 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 6 | 3 | 3 | 3 | 5 | 4 | 7 | 5 | 2 | 3 | -1 | 55 | 0 | 55 | 0 | 0 | 0
| Ajouter la focntionnalité pour la gestion des notificaitons - fréquence | 0% | 0% | 100% | 0% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 3 | 2 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0
| Ajout de l'affichage de la page dans le vue global | 100% | 0% | 0% | 0% | 0% | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0
| Ajouter la fonctionnalité seulent la priorité des notifications(ex. examen - notification 3f par semaine, quiz - notifiaction 1-2f par semaine) | 0% | 0% | 100% | 0% | 0% | 5 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 3 | 2 | 2 | 0 | 5 | 0 | 5 | 0 | 0 | 0
11 | Gestion des notifications
| Ajouter la préférances des notifications - matin, soir,etc | 0% | 0% | 100% | 0% | 0% | 8 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 3 | 5 | 3 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 6 | 0 | 6 | 0 | 0 | 0
| Ajouter la fréquences pour tous les notifications, peu importe la priorité | 0% | 0% | 100% | 0% | 0% | 3 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Desactiver les notifications au besoin par utilisateur pour X temps | 0% | 0% | 100% | 0% | 0% | 3 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | 0% | 0% | 2: 0; 4: 0; 6: 0; 8: 0; 10: 0; 12: 0; 14: 0; 16: 0; 18: 0; 20: 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | 0% | 0% | 2: 0; 4: 0; 6: 0; 8: 0; 10: 0; 12: 0; 14: 0; 16: 0; 18: 0; 20: 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | 0% | 0% | 2: 0; 4: 0; 6: 0; 8: 0; 10: 0; 12: 0; 14: 0; 16: 0; 18: 0; 20: 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | 0% | 0% | 2: 0; 4: 0; 6: 0; 8: 0; 10: 0; 12: 0; 14: 0; 16: 0; 18: 0; 20: 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | 0% | 0% | 2: 0; 4: 0; 6: 0; 8: 0; 10: 0; 12: 0; 14: 0; 16: 0; 18: 0; 20: 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | 0% | 0% | 2: 0; 4: 0; 6: 0; 8: 0; 10: 0; 12: 0; 14: 0; 16: 0; 18: 0; 20: 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on AT9: Arina: Dimanche 03/11
Note on Z10: Effort left went up after some new work has been discovered
Note on B11: Id of the story. To simplify linking to the product backlog

## team
Prénom | Nom | email | nickname
Oryna | Kubarieva | kubarieva.oryna@courrier.uqam.ca | Oryna
Aziz | Thiam | thiam.demba_aziz@courrier.uqam.ca | Aziz
Joana | Munyaneza | munyaneza_mutunge.ursule_joana@courrier.uqam.ca | Joana
Kenny | Kenfack | kenfack_nandjou.steve_marvyn@courrier.uqam.ca | Kenny
Romuald | Sokoujou | kenfack_nandjou.steve_marvyn@courrier.uqam.ca | Romuald